## Receipt IDA-NUC
AFRICA CENTRE OF EXCELLENCE IN PHYTOMEDICINE RESEARCH & DEVELOPMENT (ACEPRD)
UNIVERSITY OF JOS
ACEPRD GRANT FUND ACCOUNT
GRANT RECEIPTS
JULY TO DECEMBER 2018
S/N | DATE | DESCRIPTION | RECEIPT | DOLLAR EQUIVALENT
|  |  | =N= | $ | %
1 | 2018-07-30 | Direct Payment through NUC to ISCON SCIENTIFIC LTD FOR PURCHASE OF LABORATORY EQUIPMENT (NMR) (Amount N35,478,000.00 @ N306/$) | 35478000 | 115941.1765
2 | 2018-08-07 | Receipt from the World Bank through Direct credit into ACEPRD CBN e-collection Naira account (Total $200,000.00 @ N305.45/$ | 61090000 | 200000
3 | 2018-10-24 | Receipt from the World Bank through Direct credit into ACEPRD CBN e-collection Naira account (Total $200,000.00 @ N306/$ | 61210000 | 200000
4 | 2018-12-18 | Direct Payment through NUC to ISCON SCIENTIFIC LTD FOR PURCHASE OF LABORATORY EQUIPMENT (ALLEGRA X30, UV-VIS SPECTROPHOTOMETERS, ETC) (Amount N74,118,700.00 @ N306/$) | 74118700 | 242217.9739
|  | TOTAL INFLOW FROM EARNINGS | 231896700 | 758159.1503
CONVERSIONS CBN DOLLAR A/C TO CBN NAIRA A/C
1 | 2018-07-04 | INFLOW FROM COVERSION OF USD $100,000.00 TO NAIRA @ N304.85 | 30485000 | 100000
|  | TOTAL INFLOW CONVERSION | 30485000 | 100000
Prepared by
Luke Ngwu (Finance Officer)

## Receipt OTHERS
AFRICA CENTRE OF EXCELLENCE IN PHYTOMEDICINE RESEARCH & DEVELOPMENT (ACEPRD)
UNIVERSITY OF JOS
ACEPRD GRANT FUND ACCOUNT
REFUNDS/OTHER RECEIPTS
JULY TO DECEMBER 2018
S/N | DATE | NAME | DESCRIPTION | RECEIPT | DOLLAR EQUIVALENT
| 2018-07-04 | MATTHEW ADENIYI ADEWALE | INFLOW FROM STUDENT (DEPOSITED IN ERROR) | 115500
| 2018-08-20 | ABAH ENE PATIENCE | INFLOW FROM STUDENT (WRONGFUL DEPOSIT) | 2500
| 2018-08-28 | ALISON MAFENG WAZIRI | INFLOW FROM STUDENT (WRONGFUL DEPOSIT) | 2000
| 2018-08-31 | AUGUSTINE KINGSLEY | INFLOW FROM STUDENT (WRONGFUL DEPOSIT) | 2000
| 2018-09-04 | JOSEPH ATANG | INFLOW FROM STUDENT (WRONGFUL DEPOSIT) | 15000
| 2018-09-24 | DAFER RETNA LEDAK | INFLOW FROM STUDENT (WRONGFUL DEPOSIT) | 15000
| 2018-09-25 | ORNDIR SYLVESTER TERLUMUN | INFLOW FROM STUDENT (WRONGFUL DEPOSIT) | 15000
| 2018-09-28 | HARUNA FREEMAN | INFLOW FROM STUDENT (WRONGFUL DEPOSIT) | 15000
| 2018-10-12 | SHATU RIMAMTARI TUKI | INFLOW FROM STUDENT (WRONGFUL DEPOSIT) | 15000
197000
| 2018-08-17 | BENJAMIN DAVOU DACHOMO | REFUND OF CASH ADVANCE | 495000
| 2018-09-11 | BENJAMIN DAVOU DACHOMO | REFUND OF CASH ADVANCE | 75666.5
| 2018-10-25 | DR DOGO GONI ABRAHIM | REFUND OF OVER PAYMENT OF FLIGHT TICKET | 61275
| 2018-11-13 | MICHAEL OGIJI | REFUND OF CASH ADVANCE | 10200
| 2018-11-19 | DR . ISHAYA Y. LONGDET | REFUND OF CASH ADVANCE | 295486
| 2018-12-19 | MONICA SOLOMON LENG | REFUND FOR CLOSING BANK CHARGES - FIDELITY BANK ACE NAIRA ACC | 28
937655.5
| 2018-12-19 | FIDELITY BANK UNIJOS ACE NAIRA ACCT | TRANSFER OF ACCOUNT CLOSING BALANCE TO CBN NAIRA A/C | 1940.14
Prepared by
Luke Ngwu (Finance Officer)

## Sources and Uses of Funds
UNIVERSITY OF JOS
AFRICA CENTRE OF EXCELLENCE IN PHYTOMEDICINE RESEARCH & DEVELOPMENT (ACEPRD)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
Statement of Sources and Uses of Funds
for the semi-annual period ending 31/12/2018
Sources of Fund | Semi-Annual Period ending 31/12/2018 | Cummulative for Financial Year End
Opening Cash Balance
Government Funds | 0
World Bank IDA Funds (Fidelity Bank Plc) | 42210.64 | 42227.64
World Bank IDA Funds (CBN Naira Account) | -540739.7419 | 30893129.3
World Bank IDA Funds (CBN USD Account) | 46184708.6931 | 0
Student Fees | 0 | 0
Others | 0 | 0
Total | 45686179.5911 | 30935356.94
Add Receipts
Government Funds | 0
World Bank IDA Funds (Deposit by NUC into ACEPRD Naira Acc in CBN) | 122300000 | 172300000
World Bank IDA Funds (Deposit by NUC into ACEPRD USD Acc in CBN) | 0 | 50000000
World Bank IDA Funds (Direct payments by NUC) | 109596700 | 137546700
Student Fees (Undergraduate fee paid in error) | 197000 | 362850
Others (Refund of Advances & others) | 937655.5 | 1064112.5
Total Financing | 278717535.0911 | 392209019.44
Less: ACE Expenditure as per Project Implementation Plan
Action Plan 1: Enhance capacity to deliver regional high quality training | 147931128.76 | 209191310.77
Action Plan 2: Enhance capacity to deliver applied research to address regional development challenges to Achieve Applied Research Excellence | 56933353.19 | 67104124.7
Action Plan 3: Build & strengthen regional and international academic partnership | 8181769 | 8181769
Action Plan 4: Build and use industry/sector partnerships to enhance impact of ACE on development and increased relevance of center education and research | 4252280 | 5436560
Action Plan 5: Enhance Governance and management of ACE and the participating universities to Achieve Center/institutional Operations and Management Excellence | 49110110.83 | 84908556.0468
Action Plan 6: Enhance Revenue generation Strategies to Strengthen Financial Stability of the Centre | 3891953.76 | 8828909.3721
Total Uses of Funds by Components | 270300595.54 | 383651229.8889
Refunds (undergraduate fee wrongly paid) | 0 | 140850
Total Uses of Funds | 270300595.54 | 383792079.8889
Closing Balances | 8416939.5511 | 8416939.5511
Government Funds | 0 | 0
World Bank IDA Funds (Fidelity Bank Plc) | 0 | 0
*World Bank IDA Funds CBN Naira Account | -1646151.48 | -1646151.48
*World Bank IDA Funds CBN USD Account | 10063091.0311 | 10063091.0311
Student Fees | 0 | 0
Others (Unremitted payments pending) | 0 | 0
Total Closing Cash Balance | 8416939.5511 | 8416939.5511

## Uses of Funds by Activity
Work on the PAD/Life of project for the period
Grand total of the funds
UNIVERSITY OF JOS
AFRICA CENTRE OF EXCELLENCE IN PHYTOMEDICINE RESEARCH AND DEVELOPMENT (ACEPRD)
AFRICA HIGHER EDUCATION CENTRES OF EXCELLENCE PROJECT
Statement of Uses of Funds By Project Activity for the period ending 31/12/ 2018
| Expenditure | Semi-Annual Period ending July to December 2018 |  |  | Cummulative for Financial Year End |  |  | Explanation of | PAD /Life of | Revised
|  | Actual | Planned | Variance | Actual | Planned | Variance | Variance | Project | PAD
COMPONENT 1
Action Plan 1: Learning Excellence | Enhance capacity to deliver regional high quality training
1.1 | Design new curriculum and get approval for new short courses | 0 | 1220000 | -1220000 | 0 | 2745000 | -2745000
1.2 | Enrol and run new short courses | 16304244.88 | 4117500 | 12186744.88 | 21406650.57 | 8387500 | 13019150.57
1.3 | Design new curriculum and get approval for Masters program | 0 | 0 | 0 | 0 | 305000 | -305000
1.4 | Enrol and run new Masters curriculum | 1619200 | 11285000 | -9665800 | 2054290 | 26382500 | -24328210
1.5 | Design new curriculum and get approval for PhD program | 0 | 0 | 0 | 0 | 0 | 0
1.6 | Enrol and run new PhD curriculum | 956000 | 11437500 | -10481500 | 2764910 | 22875000 | -20110090
1.7 | e-learning platform development | 365750 | 11285000 | -10919250 | 28535750 | 103547500 | -75011750
1.8 | Running of English Second Language courses | 864500 | 2135000 | -1270500 | 1384500 | 6405000 | -5020500
1.9 | Upgrade and refurbishment of Learning Facilities/Resources | 13123599.88 | 9912500 | 3211099.88 | 29390329.24 | 32025000 | -2634670.76
1.10 | Curriculum development of English as Second language | 0 | 0 | 0 | 0 | 0 | 0
1.11 | Hostel accommodation at the University for students | 30852984 | 11285000 | 19567984 | 35628504 | 58865000 | -23236496
1.12 | Improving Learning Equipment | 83844850 | 12200000 | 71644850 | 88026376.96 | 36600000 | 51426376.96
| Subtotal | 147931128.76 | 74877500 | 73053628.76 | 209191310.77 | 298137500 | -88946189.23
Action Plan 2: Applied Research | Enhance capacity to deliver applied research to address regional development challenges
2.1 | Applied research skills for faculty and students | 9122339 | 7930000 | 1192339 | 9122339 | 19672500 | -10550161
2.2 | Field sample study and collection | 0 | 1220000 | -1220000 | 0 | 1830000 | -1830000
2.3 | Lab based sample analysis for students (basic lab equipment) | 7017549.76 | 3965000 | 3052549.76 | 10573239.76 | 13420000 | -2846760.24
2.4 | Publication submission & Seed Grant to Faculty/Students | 236628.4 | 4575000 | -4338371.6 | 315828.4 | 30500000 | -30184171.6
2.5 | Maintaining animal facility for laboratory tests | 0 | 2135000 | -2135000 | 175620 | 7015000 | -6839380
2.6 | Core specialized research equipment | 40556836.03 | 1982500 | 38574336.03 | 45967097.54 | 11895000 | 34072097.54
2.7 | Center monthly seminar | 0 | 366000 | -366000 | 0 | 732000 | -732000
2.8 | Improving Research environment | 0 | 2135000 | -2135000 | 950000 | 11285000 | -10335000
| Subtotal | 56933353.19 | 24308500 | 32624853.19 | 67104124.7 | 96349500 | -29245375.3
Action Plan 3: Academic Partnership | Build & strengthen regional and international academic partnership
3.1 | Annual partner site visit | 3278119 | 1525000 | 1753119 | 3278119 | 1677500 | 1600619
3.2 | Regional Student Exchange | 0 | 0 | 0 | 0 | 3431250 | -3431250
3.3 | Regional Faculty Exchange | 0 | 7167500 | -7167500 | 0 | 7167500 | -7167500
3.4 | Training by international faculty to build UNIJOS capacity | 4903650 | 2287500 | 2616150 | 4903650 | 2287500 | 2616150
3.5 | Center combined regional and international research conference for students and faculty | 0 | 4803750 | -4803750 | 0 | 4803750 | -4803750
3.6 | Regional Center Research Conference | 0 | 0 | 0 | 0 | 0 | 0
3.7 | Project management committee meeting (bi-weekly) | 0 | 0 | 0 | 0 | 0 | 0
3.8 | Outreach events targeting women and minorities | 0 | 11056250 | -11056250 | 0 | 20587500 | -20587500
| Subtotal | 8181769 | 26840000 | -18658231 | 8181769 | 39955000 | -31773231
Action Plan 4: Industry/Sector partnership | Build and use industry/sector partnerships to enhance impact of ACE on development and increased relevance of center education and research
4.1 | Industry Networking events | 4252280 | 10675000 | -6422720 | 5436560 | 23790000 | -18353440
| Subtotal | 4252280 | 10675000 | -6422720 | 5436560 | 23790000 | -18353440
Action Plan 5: Governance/management Excellence | Enhance Governance and management of ACE and the participating universities to Achieve Center/institutional Operations and Management Excellence
5.1 | Center Operational Cost | 8717963 | 8418000 | 299963 | 19008964.0468 | 18544000 | 464964.0468
5.2 | Vehicle purchase, fuel, maintenance | 355550 | 2135000 | -1779450 | 941780 | 4498750 | -3556970
5.3 | International Advisory Board meeting | 0 | 0 | 0 | 0 | 5673000 | -5673000
5.4 | Regional Advisory Board meeting | 4221797.6 | 4346250 | -124452.4 | 4221797.6 | 8692500 | -4470702.4
5.5 | Center Management Training | 30181739.23 | 16775000 | 13406739.23 | 52408662.1 | 31872500 | 20536162.1
5.6 | Accreditation | 5633061 | 16317500 | -10684439 | 8327352.3 | 30195000 | -21867647.7
| Subtotal | 49110110.83 | 47991750 | 1118360.83 | 84908556.0468 | 99475750 | -14567193.9532
Action Plan 6: Financial Stability | Enhance Revenue generation Strategies to Strengthen Financial Stability of the Centre
6.1 | Farm cultivation management and expansion | 3891953.76 | 4346250 | -454296.24 | 8828909.3721 | 8921250 | -92340.6279
| Subtotal | 3891953.76 | 4346250 | -454296.24 | 8828909.3721 | 8921250 | -92340.6279
| GRAND TOTAL USES OF FUNDS | 270300595.54 | 189039000 | 81261595.54 | 383651229.8889 | 566629000 | -182977770.1111
| NOTE |  | 0
1 | Exchange Rate applied to arrive at Naira value of planned is N305/$.
2 | Exchange Rate for the expenditure is average of N305/$.
Work on the PAD/Life of project for the period
Grand total of the funds