AFRICA CENTRE OF EXCELLENCE IN PHYTOMEDICINE RESEARCH AND DEVELOPMENT

UNIVERSITY OF JOS

DATE:	 11th August, 2016

KEY INFORMATION ON THE PROJECT

| Project Name and State | ACE in Phytomedicine, Research and Development/Plateau |
| --- | --- |
| Project ID | ACE 033 |
| IDA Credit/Grant No. |  |
| Implementing Agency | University of Jos |
| Effectiveness Date | July 2015 |
| Closing Date | 2018 June |
| Credit/Grant Amount | $7,414,223.00 |
| Project Duration | 4 years |
| Remaining Period to Closing | 3 years |
| Disbursed Amount to date & Percentage | N147,172,326.55 (10%) |
| Period Covered by Review | April – June 2016 |
| Internal Auditor | Njin, Naansel Paul |

EXECUTIVE SUMMARY

A regular audit of the Centre’s activities was carried out as the activities were being performed. Records checked and examined include the following.

- Payment Vouchers

- Journal Vouchers

- Bank Statements and Reconciliation

- Implementation plan and Work plan

- Financing Agreement

- Statement of uses of Funds by project activities and variations thereof.

- Interim Financial Report.

KEY FINDINGS

- A number of activities were not carried out during the period under review (Action Plans 1-6). This will delay project implementation.

- There was significant variance on all the action plans (1-6). These were as a result of non-receipt of budgeted fund.

- A number of Advances are still unretired. The Accountant has taken action to spur the staff to retire the advances. He has been advised to commence deductions from the salaries of staff that have delayed retirement.

- Project funds are used for the purpose intended.

IA REVIEW

BUDGETING

- There were significant variances between the budget and actual expenditure during the quarter, both by component and by category. Most of the activities planned for were not executed. The achievement of the agreed work plan and the overall development objective may be delayed due to the non-performance of the budget variables.

- The disbursement for this period is yet to be received from the World Bank.

- The project fund is not included in the University budget.

RECOMMENDATIONS

The release of funds from the World Bank should be timely to reduce delay in project implementation.

MANAGEMENT RESPONSE

ACCOUNTING

- The accounting system is adequate. The system has been integrated with the University’s Financial System (SAGE ERP 1000) and staff have been trained. It will soon be put into use.

- Project books of accounts and accounting records were adequately kept.

- Pre-payment audit was carried out during the period under review. Vouchers had adequate supporting documents.

- External Audit of the 2015 accounts has been carried out though not included in the University’s Financial Statements.

- The project account is yet to be transferred to the Treasury Single Account in line with Federal Government directives.

RECOMMENDATION

- The accounting software (SAGE ERP 1000) should immediately be put into use to ease processing of reports.

- The project account should be transferred to the Central Bank in line with Federal Government Policy of Treasury Single Account to avoid sanctions. (Follow up with the Bursar).

MANAGEMENT RESPONSE

-The 2015 external audit of the University is yet to be carried out. The centre’s audited accounts will be incorporated at the appropriate time.

-The centre has just been recently informed that a dedicated account has been opened for the centre. The account will be operational in due course when all logistics are concluded.

INTERNAL CONTROLS

- There was adequate segregation of duties, approval and authorization procedures.

- The Audit Committee is not functional.

- Assets are yet to be insured.

- Some advances are yet to be retired for the quarter.

UNRETIRED ADVANCES

| DOA | NAME | AMOUNT =N= | PURPOSE |
| --- | --- | --- | --- |
| 06/11/15 | Prof. J. Aguiyi | 236,000.00 | Retur Ticket to Ghana ACE/AAU Training |
| 22/12/15 | Yakubu Gomos | 50,000.00 | Media & Comm. Advert |
| 12/02/16 | Olufemi Domkap | 346,800.00 | Dros Africa Workshop |
| 22/02/16 | Kollo John | 554,993.40 | Dors Africa Workshop (Air Ticket) |
| 22/02/16 | Isa Mallo | 41,450.00 | International Research Conference |
| 14/03/16 | Prof. J. C. Aguiyi | 51,500.00 | Training |
| 14/04/16 | Roseline B. Ikilama | 29,795.40 | Publication in International Jounal |
| 17/05/16 | Ponchang A. Wuyep | 499,191.00 | Return Ticket & Visa to Spain |

RECOMMENDATIONS

- Project Assets should be fully insured. The University Management should be notified on this please.

- The Functioning of the Audit Committee is long overdue. It should be functional as a matter of urgency please.

- Deductions should commence from the salaries of those with outstanding advances.

- Staff with unretired advances should not be granted another advance.

FUNDS FLOW

- IDA funds are yet to be received for the current period as budgeted.

- Statement of Expenditure is attached.

FINANCIAL REPORTING

- The Reports generated were prepared using World Bank templates.

EXTERNAL AUDIT

- The external audit of 2015 account has been concluded and submitted to the Bank.

ASSETS PROCURED

- Rugs, Filing Cabinet for ACEPRD Centre			105,727.00

- Executive Tables and Chairs for ACEPRD Centre		205,000.00

- 2numbers Bookshelves for ACEPRD Centre			161,600.00

- SAGE ERP 1000 (Accounting Software)			2,271,685.00

PROCUREMENT ACTIVITIES

| S/NO | NAME OF SUPPLIER | ITEM | UNIT | AMOUNT |
| --- | --- | --- | --- | --- |
| 1 | Medicom Laboratory Nig. Ltd. | Chemicals & Reagents | ACEPRD Centre | 834,500.00 |
| 2 | Glo-Gin Investment Nig. Ltd. | Chemicals & Reagents | Pharmacognosy, Biochem. | 1,763,700.00 |
| 3 | Wardgate Ventures Nig. | Chemicals & Reagents | Pharmacognosy, Microbiology | 251,100.00 |
| 4 | Narison West Africa Ltd. | Chemicals & Reagents | Pharmacognosy, Microbiology | 118,850.00 |
| 5 | Macchennason Nig. Ltd. | Chemicals & Reagents | Pharmacognosy, | 59,500.00 |
| 6 | Yokel’s International Co Ltd. | Chemicals & Reagents | Biochem. | 254,000.00 |
| 7 | Medicom Laboratory Nig. Ltd. | Equipment | Pharmacognosy | 3,500,000.00 |
| 8 | Defash Ltd. | Equipment | Pharmacology | 12,112,500.00 |
| 9 | MacChennason Nig. Ltd. | Glass Wares | Biochem. | 33,800.00 |
| 10 | Yokel’s International Co. Ltd. | Glass Wares | Biochem. | 13,400.00 |
| 11 | Hubflux Digital Solutions | Laptop & Computer Appliances | ACEPRD | 2,514,750.00 |
| 12 | Hubflux Digital Solutions | Starboard Interactive Whiteboard | ACEPRD | 2,315,250.00 |
| 13 | Sunnyside Solar Nig. Ltd. | Power Back up-Inverter | ACEPRD | 2,309,527.50 |
| 14 | Obimgoods Enterprise | Office Equipment | ACEPRD | 442,000.00 |
| 15 | Northsouth Systems Ltd. | Installation of SAGE ERP 1000 Package | ACEPRD | 2,271,685.00 |

PERSONS MET IN COURSE OF Review

- Project Accountant

- Project Administration

- Procurement Officer

Sign: 	Njin, Naansel Paul

Internal Auditor