AFRICA CENTRE OF EXCELLENCE IN PHYTOMEDICINE RESEARCH AND DEVELOPMENT

UNIVERSITY OF JOS

DATE:    14th November, 2016

KEY INFORMATION ON THE PROJECT

| Project Name and State | ACE in Phytomedicine and Research Development/Plateau |
| --- | --- |
| Project ID | ACE 033 |
| IDA Credit/Grant No. |  |
| Implementing Agency | University of Jos |
| Effectiveness Date | July 2015 |
| Closing Date | 2018 June |
| Credit/Grant Amount | $7,414,223.00 |
| Project Duration | 4 years |
| Remaining Period to Closing | 2 1/2 years |
| Disbursed Amount to date & Percentage | N147,172,326.55 (10%) |
| Period Covered by Review | July – September 2016 |
| Internal Auditor | Njin, Naansel Paul |

EXECUTIVE SUMMARY

A regular audit of the Centre’s activities was carried out as the activities were being performed. Records checked and examined include the following.

- Payment Vouchers

- Journal Vouchers

- Bank Statements and Reconciliation

- Implementation plan and Work plan

KEY FINDINGS

- A large number of activities were not carried out during the period under review (Action Plans 1-6). This will delay project implementation.

- A number of Advances are still unretired. The Accountant has been advised to commence deductions from the salaries of such staff.

- Project funds are used for the purpose intended.

- Variances were not computed for the period under review.

IA REVIEW

BUDGETING

- Variances for the quarter were not computed.

- The project fund is not included in the University budget.

RECOMMENDATIONS

Variances should be computed and submitted quarterly please.

Project funds should be included in University's next year's budget.

MANAGEMENT RESPONSE

The work on IFR is in progress and could not be completed before the date line due to circumstances beyond our control.

Noted; To include the budget in 2017 .

ACCOUNTING

- The accounting system is adequate.

- Project books of accounts and accounting records were adequately kept.

- Pre-payment audit was carried out during the period under review. Vouchers had adequate supporting documents.

- The project account is yet to be transferred to the Treasury Single Account in line with Federal Government directives.

RECOMMENDATIONS

- The project account should be transferred to the Central Bank in line with Federal Government Policy of Treasury Single Account to avoid sanctions. (Follow up with the Bursar).

MANAGEMENT RESPONSE

Account opened for the centre with Central Bank of Nigeria .Funds expected fro NUC.

INTERNAL CONTROLS

- There was adequate segregation of duties, approval and authorization procedures.

- The Audit Committee is not functional.

- Assets are yet to be insured.

- Some advances are yet to be retired for the quarter.

UNRETIRED ADVANCES

| DOA | NAME | AMOUNT =N= | PURPOSE |
| --- | --- | --- | --- |
| 06/11/15 | Prof. J. Aguiyi | 236,000.00 | Return Ticket to Ghana ACE/AAU Training |
| 12/02/16 | Olufemi Domkap | 346,800.00 | Dros Africa Workshop |
| 22/02/16 | Kollo John | 554,993.40 | Dros Africa Workshop (Air Ticket) |
| 14/03/16 | Prof. J. C. Aguiyi | 51,500.00 | Training |
| 14/04/16 | Roseline B. Ikilama | 29,795.40 | Publication in International Journal |
| 17/05/16 | Ponchang A. Wuyep | 499,191.00 | Return Ticket & Visa to Spain |
| 11/07/16 | Innocent Damwan | 75,113.50 | Office rug and cabinet |
| 25/07/16 | E.O. Ekwere | 834,507.00 | Air tickets to Ouagadougou outreach |
| 25/07/16 | Monica Lengs | 160,900.00 | Pumping machine, seedlings, fertilizer |
| 14/07/16 | Samuel Otokpa Ede | 60,000.00 | Biotech Automatic micro pippettes |

RECOMMENDATIONS

- Project Assets should be fully insured as a matter of urgency please.

- The Functioning of the Audit Committee is long overdue. It should be functional as a matter of urgency please.

- Deductions should commence from the salaries of those with outstanding advances.

- Staff with unretired advances should not be granted another advance.

FUNDS FLOW

- IDA funds are yet to be received for the current period as budgeted.

- Statement of Expenditure is attached.

FINANCIAL REPORTING

- The Reports generated were prepared using World Bank templates.

EXTERNAL AUDIT

- The external audit of 2015 account has been concluded and submitted to the Bank.

PROCUREMENT ACTIVITIES

No activity within the quarter.

Some of the executed projects were paid for during the period.

PERSONS MET IN COURSE OF Review

- Project Accountant

- Project Administration

- Procurement Officer

Sign:     Njin, Naansel Paul

Internal Auditor